## Cover Page
QA TEST DOCUMENTATION
othoba.com E-Commerce Platform
| Prepared By | MD Mahedy Hasan
| Website | https://othoba.com
| Document | Test Plan ¦ Scenarios ¦ Metrics ¦ Mind Map
| Date | May 2026
| Total TCs | 29 Test Cases
| Bugs Found | 5 Defects Identified
Naiem.Website ¦ https://othoba.com ¦ © 2026 MD Mahedy Hasan

## Test Plan
🧪 TEST PLAN — othoba.com
1. PROJECT OVERVIEW
| Project Name | othoba.com – E-Commerce Platform QA
| Prepared By | MD Mahedy Hasan
| Website URL | https://othoba.com
| Document Version | v1.0
| Test Period | May 2026
2. SCOPE OF TESTING | Testing Type | Functional, UI, Browser Compatibility, Regression
| IN SCOPE | Account/Browser Compatibility, Register, Login/Logout, Navigation Bar, Header (Search, Wishlist, Compare), Product Page, Cart, UI Elements
| OUT OF SCOPE | Payment Gateway, Admin Panel, API Backend, Performance/Load Testing, Mobile Native App
| Test Environment | Production – https://othoba.com ¦ Browsers: Chrome, Firefox, Edge, Brave
3. TEST OBJECTIVES | Devices | Desktop Web Browser (Primary)
✔ Verify all registration and login flows behave as per requirements
✔ Ensure UI elements match design specifications (font, color, size)
✔ Validate navigation bar and header functionality
✔ Confirm product search, cart, wishlist, and compare features work correctly
✔ Identify and document all defects with screenshots
4. ENTRY & EXIT CRITERIA | ✔ Ensure cross-browser compatibility across 4 major browsers
| Entry Criteria | Test environment is available; Test cases are reviewed and approved; Test data is prepared
| Exit Criteria | All critical/high test cases executed; No open Critical bugs; Test summary report approved
| Suspension | Critical environment failures blocking 50%+ of test execution
5. RISK & MITIGATION | Resumption | Environment restored and verified by DevOps/Dev team
| Risk | Severity | Mitigation
| Unstable test environment | High | Coordinate with Dev team for stable build
| Missing test data | Medium | Prepare test data sets in advance
| Incomplete requirements | Medium | Regular sync with stakeholders
| Time constraints | Low | Prioritise critical path test cases

## Test Scenarios
📋 TEST SCENARIOS — othoba.com
Prepared by: MD Mahedy Hasan ¦ https://othoba.com
# | Module | Type | Scenario Description | Expected Outcome | Priority
1 | Account | Browser Compat | Verify site loads & functions correctly across Chrome, Firefox, Edge, Brave | Site loads without errors in all 4 browsers | High
2 | Register | Functional | Verify invalid phone number shows error popup | Error: "Input valid phone number" | High
3 | Register | Functional | Verify invalid email address shows error popup | Error: "Invalid email address" | High
4 | Register | Functional | Verify gender field is mandatory | Error when gender not selected | Medium
5 | Register | Functional | Verify first name field is mandatory | Error: "First name is required" | High
6 | Register | Functional | Verify second name field is mandatory | Error: "Second name is required" | High
7 | Register | Functional | Verify date of birth (Date) field is mandatory | Error: "Date of birth is required" | Medium
8 | Register | Functional | Verify date of birth (Month) field is mandatory | Error: "Date of birth is required" | Medium
9 | Register | Functional | Verify date of birth (Year) field is mandatory | Error: "Date of birth is required" | Medium
10 | Register | Functional | Verify password field is mandatory | Error: "Password is required" | High
11 | Register | Functional | Verify confirm password field is mandatory | Error: "Confirm password is required" | High
12 | Register | UI | Verify all registration UI elements match design specs | Font size, color, asterisk marks match spec | Medium
13 | Login | Functional | Verify successful login with correct credentials | User logs in and is redirected to homepage | Critical
14 | Login | Functional | Verify login with blank fields shows error | Error: "Please enter your email or phone" | High
15 | Login | Functional | Verify login with wrong password shows error | Error: "The password is incorrect" | High
16 | Login | Functional | Verify login with wrong phone shows error | Error: "The phone number is incorrect" | High
17 | Login | Functional | Verify Forgot Password link navigates correctly | User is redirected to Forgot Password page | High
18 | Login | UI | Verify all login page elements and fields are present | All mandatory fields displayed correctly | Medium
19 | Navigation Bar | Functional | Verify 'GET APP DEALS' redirects to App download/Play Store | User is redirected to App download page | Medium
20 | Navigation Bar | Functional | Verify 'Sell on othoba' redirects to login/signup form | User is redirected to login/signup page | Medium
21 | Header | UI | Verify logo is clearly visible, aligned, and links to homepage | Logo displays correctly and links to homepage | Medium
22 | Header | Functional | Verify valid product search returns relevant results | Search results show relevant products | High
23 | Header | Functional | Verify wishlist icon redirects to wishlist page | User is redirected to wishlist page | Medium
24 | Header | Functional | Verify compare icon functionality | Selected products are displayed for comparison | Medium
25 | Product Page | Functional | Verify 'Add to Cart' adds the product and shows success message | Product added to cart; success message shown | Critical
26 | Product Page | UI | Verify product images zoom on hover | Image zooms clearly on mouse hover | Low
27 | Cart | Functional | Verify increasing product quantity updates price correctly | Price updates proportionally with quantity | High
28 | Cart | Functional | Verify removing item from cart clears/updates cart | Item removed; cart updates correctly | High
29 | Logout | Functional | Verify clicking Logout signs user out and redirects | User logged out; redirected to homepage/login | High

## Test Metrics
📊 TEST METRICS DASHBOARD — othoba.com
Prepared by: MD Mahedy Hasan ¦ https://othoba.com
| 29 | 21 | 4 | 4 | 72% | 5
| Module | Total | Passed | Failed | Not Run | Pass %
| Account | 1 | 1 | 0 | 0 | 100%
| Register | 11 | 7 | 4 | 0 | 63.64%
| Login | 6 | 6 | 0 | 0 | 100%
| Navigation Bar | 2 | 2 | 0 | 0 | 100%
| Header | 4 | 4 | 0 | 0 | 100%
| Product Page | 2 | 2 | 0 | 0 | 100%
| Cart | 2 | 2 | 0 | 0 | 100%
| Logout | 1 | 1 | 0 | 0 | 100%
| TOTAL | 29 | 21 | 4 | 4 | 72.41%
BUG SUMMARY
| TC# | Module | Feature | Issue Found | Severity | Status
| 3 | Register | Auth | Invalid email allows registration | High | Open
| 4 | Register | Auth | Gender not required – user registers anyway | Medium | Open
| 6 | Register | Auth | Blank second name allows registration | High | Open
| 13 | Login | Auth | Blank-field error message wording mismatch | Low | Open
| 18 | Register | UI | First Name UI issue (font/color mismatch) | Medium | Open

## Mind Map
🗺️ TEST MIND MAP — othoba.com
Prepared by: MD Mahedy Hasan ¦ https://othoba.com
🌐 othoba.com Test Coverage
🔐 Auth |  | 🔀 Navigation |  |  | 🏠 Header |  | 🛒 Shopping | 🖥️ UI / UX
Register 11 TCs |  | GET APP DEALS |  |  | Logo |  | Product Page | Browser Compat
Login 6 TCs |  | Sell on othoba |  |  | Search |  | Add to Cart | Design Specs
Logout 1 TC |  |  |  |  | Wishlist |  | Cart Qty | Image Zoom
[5 empty] | Compare |  | Remove Item
🟦 Functional Tests | 🟩 Shopping Tests |  | 🟨 UI Tests |  |  | 🟣 Header Tests | 🔵 Navigation

## Test case
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status
1 | Account | Browser Compatibility Testing | Account | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Mozilla Firefox, Microsoft Edge, Brave. | 1. Go to different browsers. 2. Search 'othoba' 3. Go to the website. |  |  | Passed
2 | Register | Function | Auth | Verify the phone number field | Should show a pop up error massage like "input vaild phone number" | Found as per expectation. | 17953162644 | 1. Go to the URL https://othoba.com/ 2. Click on the register icon. 3.Fill in all valid information in the registration form except the phone number. | Clikc here |  | Passed
3 | Register | Function | Auth | Verify vaild email address. | Should show a pop-up error message for "an invalid email address" | register successfully. | me@ofjgm.com | 1. Go to the URL https://othoba.com/ 2. Click on the register icon. 3.Fill in all valid information in the registration form except the email address. | Click here |  | Failed
4 | Register | Function | Auth | Verify the gender field | Should show an error when gender is not selected. | register successfully. | Not checked any option Male & Female | 1. Go to the URL https://othoba.com/ 2. Click on the register icon. 3. Fill in all required fields except the gender selection | Click here |  | Failed
5 | Register | Function | Auth | Verify the First name field | Should show an pop-up error message "fill the first name" or "frist name is required." | Found as per expectation. | Left the field blank. | 1. Go to the URL https://othoba.com/ 2. Click on the register icon. 3. Fill in all required fields except the first name field. | Click here |  | Passed
6 | Register | Function | Auth | Verify the second name field. | Should show an pop-up error message "fill the second name" or "second name is required." | register successfully. | Left the field blank. | 1. Go to the URL https://othoba.com/ 2. Click on the register icon. 3. Fill in all required fields except the second name field. | Click here |  | Failed
7 | Register | Function | Auth | Verify Date of birth section "DATE" | Should show an pop-up error message "Date of birth is required". | Found as per expectation. | Left the field blank. | 1. Go to the URL https://othoba.com/ 2. Click on the register icon. 3. Fill in all required fields except the Date dropdown field. | Click here |  | Passed
8 | Register | Function | Auth | Verify Date of birth section "Month" | Should show an pop-up error message "Date of birth is required". | Found as per expectation. | Left the field blank. | 1. Go to the URL https://othoba.com/ 2. Click on the register icon. 3. Fill in all required fields except the Month dropdown field. | Click here |  | Passed
9 | Register | Function | Auth | Verify Date of birth section "Year" | Should show an pop-up error message "Date of birth is required". | Found as per expectation. | Left the field blank. | 1. Go to the URL https://othoba.com/ 2. Click on the register icon. 3. Fill in all required fields except the Year dropdown field. | Click here |  | Passed
10 | Register | Function | Auth | Verify password field | Should show an pop-up error message "Password is required". | Found as per expectation. | Left the field blank. | 1. Go to the URL https://othoba.com/ 2. Click on the register icon. 3. Fill in all required fields except the Password field. | Click here |  | Passed
11 | Register | Function | Auth | Verify confirm password field | Should show an pop-up error message "Confirm password is required". | Found as per expectation. | Left the field blank. | 1. Go to the URL https://othoba.com/ 2. Click on the register icon. 3. Fill in all required fields except the Confirm Password field. | Click here |  | Passed
12 | Login | Function | Auth | Verify that the user will be able to log in with their account with the correct credential | User should be able to login with correct credintial | Found as per expectation. | Correct Phone number & password | 1. Go to the URL https://othoba.com/ 2. Click on the Login icon. 3. Fill the phone number and password field. | Click here |  | Passed
13 | Login | Function | Auth | Verify that the user will be able to login with enter any information. | Should show an pop-up error message"Please enter your email or phone number " | Found not exactly as pop-up message,it shows "Please enter your email" | Left the field blank. | 1. Go to the URL https://othoba.com/ 2. Click on the Login icon. 3. Left the field blank phone number and password. 4.Click on Login button | Click here |  | Passed
14 | Login | Function | Auth | Verify that the user will be able to log in with their account with the incorrect password. | Should show an pop-up error message"The password is incorrect " | Found as per expectation. | phone:01795316264 pw:wrong pw | 1. Go to the URL https://othoba.com/ 2. Click on the Login icon. 3. Fill the phone number and wrong password. 4.Click on Login button | Click here |  | Passed
15 | Login | Function | Auth | Verify that the user will be able to log in with their account with the incorrect phone number. | Should show an pop-up error message"The phone number is incorrect " | Found as per expectation. | phone:017953162640 pw:right pw | 1. Go to the URL https://othoba.com/ 2. Click on the Login icon. 3. Fill with wrong phone number and password. 4.Click on Login button | Click here |  | Passed
16 | Login | Function | Auth | Verify that "Forgot password" working or not. | Should go to the forgot password page | Found as per expectation. | N/A | 1. Go to the URL https://othoba.com/ 2. Click on the Login icon. 3. Click on Forgot password button |  |  | Passed
17 | Register | Function | Auth | Verify all login-related elements and fields are present on the login page. | Should be present the mandatory field . | Found as per expectation. | None | 1. Go to the URL https://othoba.com/ 2. Click on the Login icon in the right corner. 3. Click the "Login" link and check the spelling and grammatical mistakes. |  |  | Passed
18 | Register | Function | Auth | Verify that the size, color, case sensitive and UI of different elements should match the specifications. | Should be as per the client requirement | First Name Problem | None | 1. Go to the URL https://othoba.com/ 2. Click on the Login icon in the right corner. 3. Click the "Login" link and check * this sign. 4.Check font size,color. | Click here |  | Failed
19 | Navigation Bar | Functional | Mobile App Link | Verify clicking "GET APP DEALS" redirects to the App download page. | Should be redirected to the App Download page or Play Store. | Found as per expectation. | None | 1. Go to the URL https://othoba.com/ 2. Click on the Get App Deals icon.. |  |  | Passed
20 | Navigation Bar | Functional | Auth | Verify clicking "Sell on othoba" redirects to the login and signup form | Should be redirected to the login and signup page . | Found as per expectation. | None | 1. Go to the URL https://othoba.com/ 2. Click on Sell on othoba icon. |  |  | Passed
21 | Header | UI | Logo | Verify the logo is clearly visible and aligned correctly. | Should be align correctly,clearly visible and link properly | Found as per expectation. | None | 1. Go to the URL https://othoba.com/ 2. Click on the othoba icon. |  |  | Passed
22 | Header | Functional | Search | Verify valid product search works properly. | Should be show vaild product when search a product | Found as per expectation. | Black shoes | 1. Go to the URL https://othoba.com/ 2. Click on search field.3.Type Black shoes.4.Click on search |  |  | Passed
23 | Header | Functional | Wishlist | Verify clicking wishlist button redirects to wishlist page. | Should be redirected to the wishlist page if any product in wishlist. | Found as per expectation. | None | 1. Go to the URL https://othoba.com/ 2. Click on wishlist icon. |  |  | Passed
24 | Header | Functional | Compare | Verify compare icon functionality works. | Should be redirected to the compare page if any products in compared for. | Found as per expectation. | Black shoes and white shoes compare | 1. Go to the URL https://othoba.com/ 2. Click on Compare icon. |  |  | Passed
25 | Product Page | Functional | Add to Cart | Verify clicking "Add to Cart" button adds the item. | Product should be added to the cart and a success message shown. | Found as per expectation. | Product | 1. Go to the URL https://othoba.com/ 2. Search a product.3.Go into product information 4. Click On "Add to cart" |  |  | Passed
26 | Product Page | UI | Product Image | Verify that product images are zooming on hover. | Image should zoom in clearly when the mouse hovers over it. | Found as per expectation. | None | 1. Go to the URL https://othoba.com/ 2. Search a product.3.Go into product information 4. Hover the mouse over the product image |  |  | Passed
27 | Cart | Functional | Cart | Verify increasing the quantity of a product in the cart. | Price should increase based on the quantity. | Found as per expectation. | Qty: 1 to 2,3 | 1. Go to the URL https://othoba.com/ 2. Search a product.3.Go into product information 4. Click On "Add to cart". 4.Increase quantity 1 to 2 |  |  | Passed
28 | Cart | Functional | Remove Item | Verify removing an item from the cart. | Item should be removed and the cart should be empty/updated. | Found as per expectation. | None | 1. Go to the URL https://othoba.com/ 2. Search a product.3.Go into product information 4. Click On "Add to cart".4.Click the remove cart icon |  |  | Passed
29 | Logout | Functional | Auth | Verify that clicking the "Logout" button signs the user out. | Should be logged out successfully and redirected to the Homepage or Login page. | Found as per expectation. | None | 1. Go to the URL https://othoba.com/ 2. Click on Logout icon |  |  | Passed

## Bug report
BUG REPORT — othoba.com ¦ MD Mahedy Hasan ¦ https://othoba.com/
Bug ID | Module | Test Case | Bug Title | Severity | Priority | Steps to Reproduce | Expected | Actual | Status | Dev Comments
BUG-001 | Register | TC-03 | Invalid Email Accepted During Registration | Critical | High | 1. Open https://othoba.com/ 2. Click Register 3. Enter me@ofjgm.com as email 4. Fill other fields correctly 5. Submit | Error: 'Please enter a valid email address' | Registration succeeded with invalid email format | Open | Needs server-side email validation
BUG-002 | Register | TC-04 | Gender Field Not Enforced | High | High | 1. Open https://othoba.com/ 2. Click Register 3. Leave Male/Female unselected 4. Fill all other fields 5. Submit | Error: 'Please select your gender' | Registration completed without gender selection | Open | Gender should be mandatory
BUG-003 | Register | TC-06 | Last Name Field Not Required | High | Medium | 1. Open https://othoba.com/ 2. Click Register 3. Leave last name blank 4. Fill all other fields 5. Submit | Error: 'Last name is required' | Registration succeeded without last name | Open | Add required validation to last name
BUG-004 | Register | TC-18 | UI Inconsistency — First Name Field Style | Medium | Low | 1. Open https://othoba.com/ 2. Click Register 3. Observe First Name field font/color/size | Field style matches design spec (consistent with other fields) | First Name field has visual inconsistency (font or color mismatch) | Open | UI alignment needed
BUG-005 | Login | TC-13 | Empty Login Error Message Mismatch | Low | Low | 1. Open https://othoba.com/ 2. Click Login 3. Leave fields blank 4. Click Login button | Error: 'Please enter your email or phone number' | Message shows only 'Please enter your email' — phone not mentioned | Open | Update error copy to include phone